## Sheet1
Key IDs | Director | ADM | Team Name | Total | Onsite | Offshore | KT Start Date | KT End Date | CW ID | ADID | RSA | CitrixLaptop | Knowledge Acquisition | Assisted Perform | Independent Perform | Steady State | Billing Start Date | Key Updates | Remarks
ProjectName_01 | Benjamin | Oliver | Team One | 3 | 4 | 3 | 2024-02-05 00:00:00 | 2024-03-05 00:00:00 | 3 | 3 | 3 | 3 | 2024-02-20 00:00:00 | 2024-02-27 00:00:00 | 2024-03-05 00:00:00 | 2024-03-06 00:00:00 | 2024-03-06 00:00:00 | KT Completed. In Steady State.
ProjectName_03 | Serenity Panickar | Noah | Team three | 3 | 0 | 3 | 2024-01-29 00:00:00 | 2024-03-15 00:00:00 | 3 | 3 | 3 | 3 | 2024-02-16 00:00:00 | 2024-03-01 00:00:00 | 2024-03-29 00:00:00 | 2024-04-01 00:00:00 | 2024-04-01 00:00:00 | KT Completed. In Steady State.
ProjectName_04 | Serenity Panickar | Noah | Team 4 | 1 | 1 | 0 | 2024-01-29 00:00:00 | 2024-03-15 00:00:00 | 1 | 1 | 1 | 1 | 2024-02-16 00:00:00 | 2024-03-01 00:00:00 | 2024-03-29 00:00:00 | 2024-04-01 00:00:00 | 2024-04-01 00:00:00 | KT Completed. In Steady State.
ProjectName_05 | James | William | Team 5 | 6 | 1 | 5 | 2024-02-07 00:00:00 | 2024-05-06 00:00:00 | 6 | 6 | 6 | 6 | 2024-03-19 00:00:00 | 2024-04-05 00:00:00 | 2024-05-06 00:00:00 | 2024-05-07 00:00:00 | 2024-05-21 00:00:00 | KT Completed. In Steady State. | Incumbent disengagement date changed to 6/28 to accommodate release schedule planned to be performed by incumbent, however steady state is negotiated to begin from 5/7 for TechM.
ProjectName_06 | Appa | Amma | Team 6 | 12 | 2 | 3

## Sheet2
First Name | Last Name | TechM mail Id | Profile Link | Email Id | Mobile | External | Submission date | Exp | Location | City | Country | Date of Joining | Customer Billing Start date | Tech M Interview Date | Interview Feedback Link | Customer Interview Date | Customer Feedback | Status | Remarks | Remarks2 | Sourced to Client date | Transition Month | ADM | Team | App Name | Skill | Technology Skill | Skill Level | FTE/Subcon
John | Doe | john.doe@techm.com | http://linkedin.com/johndoe | john.doe@gmail.com | 1234567890 | No | 2023-01-15 00:00:00.000000 | 5 | New York | New York | USA | 2023-02-01 00:00:00.000000 | 2023-03-01 00:00:00.000000 | 2023-02-15 00:00:00.000000 | http://feedback.com/johndoe | 2023-02-20 00:00:00.000000 | Positive | Active |  |  | 2023-03-05 00:00:00.000000 | March | Smith | TeamA | AppA | Python | Advanced | High | FTE
Jane | Smith | jane.smith@techm.com | http://linkedin.com/janesmith | jane.smith@gmail.com | 987654321 | Yes | 2023-01-20 00:00:00.000000 | 3 | San Francisco | San Francisco | USA | 2023-02-05 00:00:00.000000 | 2023-03-05 00:00:00.000000 | 2023-02-20 00:00:00.000000 | http://feedback.com/janesmith | 2023-02-25 00:00:00.000000 | Neutral | Active | Needs Improvement |  | 2023-03-10 00:00:00.000000 | March | Johnson | TeamB | AppB | Java | Intermediate | Medium | Subcon
Emily | Jones | emily.jones@techm.com | http://linkedin.com/emilyjones | emily.jones@gmail.com | 1122334455 | No | 2023-01-25 00:00:00.000000 | 7 | Chicago | Chicago | USA | 2023-02-10 00:00:00.000000 | 2023-03-10 00:00:00.000000 | 2023-02-25 00:00:00.000000 | http://feedback.com/emilyjones | 2023-03-01 00:00:00.000000 | Positive | Inactive |  |  | 2023-03-15 00:00:00.000000 | March | Williams | TeamC | AppC | C# | Advanced | High | FTE
Michael | Brown | michael.brown@techm.com | http://linkedin.com/michaelbrown | michael.brown@gmail.com | 2233445566 | Yes | 2023-01-30 00:00:00.000000 | 10 | Boston | Boston | USA | 2023-02-15 00:00:00.000000 | 2023-03-15 00:00:00.000000 | 2023-03-05 00:00:00.000000 | http://feedback.com/michaelbrown | 2023-03-10 00:00:00.000000 | Negative | Active | Needs Improvement |  | 2023-03-20 00:00:00.000000 | March | Davis | TeamD | AppD | JavaScript | Intermediate | Medium | Subcon
Sarah | Wilson | sarah.wilson@techm.com | http://linkedin.com/sarahwilson | sarah.wilson@gmail.com | 3344556677 | No | 2023-02-01 00:00:00.000000 | 2 | Los Angeles | Los Angeles | USA | 2023-02-20 00:00:00.000000 | 2023-03-20 00:00:00.000000 | 2023-03-10 00:00:00.000000 | http://feedback.com/sarahwilson | 2023-03-15 00:00:00.000000 | Positive | Inactive |  |  | 2023-03-25 00:00:00.000000 | March | Martinez | TeamE | AppE | Ruby | Beginner | Low | FTE

## Sheet3
Profile uploaded in Large Deal Coupa | Details sent to VAIRA | Tech M allocation | Coupa Request Sent to PMO | Emp ID | Band | Resource Name | Location | App Name | Skills | Tech M E-mail ID | UPS E-mail ID | Phone # | New RM change is completed - Yes or NO | VPN Ticket ID | Citrix Ticket ID | RM/IBU Head approval - Aproved/ Pending | CW ID | Challenge Q&A Setup | UPS E-mail access | AD ID | UPS Laptop | Static IP Whitelisting | Citrix installed in system | VPN installed in system | APRS e-mail | RSA activation | Citrix license | Check point VPN Access | Zscalar policy | UPS Teams access | Remote Desktop IP address | ITAS Access | PAR ID | Coupa end date | Data Protection (SS1369) | Sexual Harassment (POSH) | Code of Ethical Business Conduct Mandate (CEBC) | Securing Our Business (SS18449) | Logistics 101 | Hacker Rank Certification | Added in Vaira's List | Lead Resource | 2nd POC | TechM Laptop (Y/N) | Citrix approval-ISG | Citrix approval-RM | Citrix approval-IBU Head | VPN | Citrix approval-RM | Citrix approval-IBU Head | UPS Laptop (Y/N) | KT Start Date | Remarks | Project
|  |  | Coupa Request | [44 empty] | approval-ISG
Yes | Yes | 50% | Yes | EMP001 | A | John Doe | New York | App1 | Java | john.doe@techm.com | john.doe@ups.com | 123-456-7890 | Yes | VPN001 | CIT001 | Approved | CW001 | Yes | Yes | AD001 | Yes | Yes | Yes | Yes | APRS001 | Yes | Yes | Yes | Yes | Yes | 192.168.0.1 | Yes | PAR001 | 2023-12-31 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Jane Smith | Alice Johnson | Yes | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2023-01-01 | All good | Project1
No | No | 30% | No | EMP002 | B | Jane Smith | London | App2 | Python | jane.smith@techm.com | jane.smith@ups.com | 234-567-8901 | No | VPN002 | CIT002 | Pending | CW002 | No | No | AD002 | No | No | No | No | APRS002 | No | No | No | No | No | 192.168.0.2 | No | PAR002 | 2024-01-31 | No | No | No | No | No | No | No | John Doe | Alice Johnson | No | Pending | Pending | Pending | No | Pending | Pending | No | 2023-02-01 | None | Project2
Yes | Yes | 70% | Yes | EMP003 | C | Bob Brown | Sydney | App3 | JavaScript | bob.brown@techm.com | bob.brown@ups.com | 345-678-9012 | Yes | VPN003 | CIT003 | Approved | CW003 | Yes | Yes | AD003 | Yes | Yes | Yes | Yes | APRS003 | Yes | Yes | Yes | Yes | Yes | 192.168.0.3 | Yes | PAR003 | 2024-02-28 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Jane Smith | John Doe | Yes | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2023-03-01 | Some remarks | Project3
No | No | 40% | No | EMP004 | D | Alice Johnson | Tokyo | App4 | C++ | alice.johnson@techm.com | alice.johnson@ups.com | 456-789-0123 | No | VPN004 | CIT004 | Pending | CW004 | No | No | AD004 | No | No | No | No | APRS004 | No | No | No | No | No | 192.168.0.4 | No | PAR004 | 2024-03-31 | No | No | No | No | No | No | No | John Doe | Jane Smith | No | Pending | Pending | Pending | No | Pending | Pending | No | 2023-04-01 | No remarks | Project4
Yes | Yes | 60% | Yes | EMP005 | E | Alice White | Paris | App5 | Go | alice.white@techm.com | alice.white@ups.com | 567-890-1234 | Yes | VPN005 | CIT005 | Approved | CW005 | Yes | Yes | AD005 | Yes | Yes | Yes | Yes | APRS005 | Yes | Yes | Yes | Yes | Yes | 192.168.0.5 | Yes | PAR005 | 2024-04-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Jane Smith | Bob Brown | Yes | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2023-05-01 | All good | Project5

## Sheet4
# | Date | Team | Resource Name | Issue Description | Owner | TechM - SPOC | Priority | Status | Resolution Comments
1 | 2024-01-01 | Team A | John Doe | Issue with application login | Jane Smith | Mike Johnson | High | Open | Investigating the root cause
2 | 2024-01-02 | Team B | Jane Smith | Database connectivity issue | Bob Brown | Alice White | Medium | In Progress | Checking database configurations
3 | 2024-01-03 | Team C | Bob Brown | Slow application performance | Alice Johnson | John Doe | Low | Resolved | Optimized the database queries
4 | 2024-01-04 | Team D | Alice Johnson | API integration failure | John Doe | Jane Smith | High | Open | Working with third-party vendor
5 | 2024-01-05 | Team E | Alice White | User interface bug in dashboard | Mike Johnson | Bob Brown | Medium | In Progress | Redesigning the UI component