## Sheet1
Key IDs | Director | ADM | Team Name | Total | Onsite | Offshore | KT Start Date | KT End Date | CW ID | ADID | RSA | CitrixLaptop | Knowledge Acquisition | Assisted Perform | Independent Perform | Steady State | Billing Start Date | Key Updates | Remarks | Interns | originalIndex
1 | Jane Smith | John Doe | Team Alpha | 10 | 4 | 6 | 2023-01-01 00:00:00 | 2023-01-10 00:00:00 | 1001 | 1001 | 2001 | 3001 | 2023-01-11 00:00:00 | 2023-02-01 00:00:00 | 2023-02-15 00:00:00 | 2023-03-01 00:00:00 | 2023-03-05 00:00:00 | Completed on time | - | 0 | 0
2 | Jane Smith | John Doe | Team Alpha | 12 | 5 | 7 | 2023-01-05 00:00:00 | 2023-01-15 00:00:00 | 1002 | 1002 | 2002 | 3002 | 2023-01-16 00:00:00 | 2023-02-05 00:00:00 | 2023-02-20 00:00:00 | 2023-03-05 00:00:00 | 2023-03-10 00:00:00 | Minor delays | - | 0 | 1
3 | Jane Smith | John Doe | Team Alpha | 8 | 3 | 5 | 2023-01-10 00:00:00 | 2023-01-20 00:00:00 | 1003 | 1003 | 2003 | 3003 | 2023-01-21 00:00:00 | 2023-02-10 00:00:00 | 2023-02-25 00:00:00 | 2023-03-10 00:00:00 | 2023-03-15 00:00:00 | On track | - | 0 | 2
4 | Jane Smith | John Doe | Team Alpha | 15 | 6 | 9 | 2023-01-15 00:00:00 | 2023-01-25 00:00:00 | 1004 | 1004 | 2004 | 3004 | 2023-01-26 00:00:00 | 2023-02-15 00:00:00 | 2023-03-01 00:00:00 | 2023-03-15 00:00:00 | 2023-03-20 00:00:00 | Completed early | - | 0 | 3
5 | Jane Smith | John Doe | Team Alpha | 10 | 4 | 6 | 2023-01-20 00:00:00 | 2023-01-30 00:00:00 | 1005 | 1005 | 2005 | 3005 | 2023-01-31 00:00:00 | 2023-02-20 00:00:00 | 2023-03-05 00:00:00 | 2023-03-20 00:00:00 | 2023-03-25 00:00:00 | On hold | - | 0 | 4
6 | Mark Lee | Mary Jones | Team Beta | 9 | 3 | 6 | 2023-02-01 00:00:00 | 2023-02-10 00:00:00 | 1006 | 1006 | 2006 | 3006 | 2023-02-11 00:00:00 | 2023-03-01 00:00:00 | 2023-03-15 00:00:00 | 2023-04-01 00:00:00 | 2023-04-05 00:00:00 | Completed on time | - | 0 | 5
7 | Mark Lee | Mary Jones | Team Beta | 11 | 4 | 7 | 2023-02-05 00:00:00 | 2023-02-15 00:00:00 | 1007 | 1007 | 2007 | 3007 | 2023-02-16 00:00:00 | 2023-03-05 00:00:00 | 2023-03-20 00:00:00 | 2023-04-05 00:00:00 | 2023-04-10 00:00:00 | Minor delays | - | 0 | 6
8 | Mark Lee | Mary Jones | Team Beta | 13 | 5 | 8 | 2023-02-10 00:00:00 | 2023-02-20 00:00:00 | 1008 | 1008 | 2008 | 3008 | 2023-02-21 00:00:00 | 2023-03-10 00:00:00 | 2023-03-25 00:00:00 | 2023-04-10 00:00:00 | 2023-04-15 00:00:00 | On track | - | 0 | 7
9 | Mark Lee | Mary Jones | Team Beta | 7 | 2 | 5 | 2023-02-15 00:00:00 | 2023-02-25 00:00:00 | 1009 | 1009 | 2009 | 3009 | 2023-02-26 00:00:00 | 2023-03-15 00:00:00 | 2023-03-30 00:00:00 | 2023-04-15 00:00:00 | 2023-04-20 00:00:00 | Completed early | - | 0 | 8
10 | Mark Lee | Mary Jones | Team Beta | 12 | 5 | 7 | 2023-02-20 00:00:00 | 2023-03-01 00:00:00 | 1010 | 1010 | 2010 | 3010 | 2023-03-02 00:00:00 | 2023-03-20 00:00:00 | 2023-04-05 00:00:00 | 2023-04-20 00:00:00 | 2023-04-25 00:00:00 | On hold | - | 0 | 9
11 | Lisa Wong | Tom White | Team Gamma | 10 | 4 | 6 | 2023-03-01 00:00:00 | 2023-03-10 00:00:00 | 1011 | 1011 | 2011 | 3011 | 2023-03-11 00:00:00 | 2023-04-01 00:00:00 | 2023-04-15 00:00:00 | 2023-05-01 00:00:00 | 2023-05-05 00:00:00 | Completed on time | - | 0 | 10
12 | Lisa Wong | Tom White | Team Gamma | 9 | 3 | 6 | 2023-03-05 00:00:00 | 2023-03-15 00:00:00 | 1012 | 1012 | 2012 | 3012 | 2023-03-16 00:00:00 | 2023-04-05 00:00:00 | 2023-04-20 00:00:00 | 2023-05-05 00:00:00 | 2023-05-10 00:00:00 | Minor delays | - | 0 | 11
13 | Lisa Wong | Tom White | Team Gamma | 11 | 5 | 6 | 2023-03-10 00:00:00 | 2023-03-20 00:00:00 | 1013 | 1013 | 2013 | 3013 | 2023-03-21 00:00:00 | 2023-04-10 00:00:00 | 2023-04-25 00:00:00 | 2023-05-10 00:00:00 | 2023-05-15 00:00:00 | On track | - | 0 | 12
14 | Lisa Wong | Tom White | Team Gamma | 13 | 6 | 7 | 2023-03-15 00:00:00 | 2023-03-25 00:00:00 | 1014 | 1014 | 2014 | 3014 | 2023-03-26 00:00:00 | 2023-04-15 00:00:00 | 2023-04-30 00:00:00 | 2023-05-15 00:00:00 | 2023-05-20 00:00:00 | Completed early | - | 0 | 13
15 | Lisa Wong | Tom White | Team Gamma | 8 | 3 | 5 | 2023-03-20 00:00:00 | 2023-03-30 00:00:00 | 1015 | 1015 | 2015 | 3015 | 2023-03-31 00:00:00 | 2023-04-20 00:00:00 | 2023-05-05 00:00:00 | 2023-05-20 00:00:00 | 2023-05-25 00:00:00 | On hold | - | 0 | 14
16 | John Brown | Anna Green | Team Delta | 12 | 5 | 7 | 2023-04-01 00:00:00 | 2023-04-10 00:00:00 | 1016 | 1016 | 2016 | 3016 | 2023-04-11 00:00:00 | 2023-05-01 00:00:00 | 2023-05-15 00:00:00 | 2023-06-01 00:00:00 | 2023-06-05 00:00:00 | Completed on time | - | 0 | 15
17 | John Brown | Anna Green | Team Delta | 10 | 4 | 6 | 2023-04-05 00:00:00 | 2023-04-15 00:00:00 | 1017 | 1017 | 2017 | 3017 | 2023-04-16 00:00:00 | 2023-05-05 00:00:00 | 2023-05-20 00:00:00 | 2023-06-05 00:00:00 | 2023-06-10 00:00:00 | Minor delays | - | 0 | 16
18 | John Brown | Anna Green | Team Delta | 14 | 6 | 8 | 2023-04-10 00:00:00 | 2023-04-20 00:00:00 | 1018 | 1018 | 2018 | 3018 | 2023-04-21 00:00:00 | 2023-05-10 00:00:00 | 2023-05-25 00:00:00 | 2023-06-10 00:00:00 | 2023-06-15 00:00:00 | On track | - | 0 | 17
19 | John Brown | Anna Green | Team Delta | 9 | 3 | 6 | 2023-04-15 00:00:00 | 2023-04-25 00:00:00 | 1019 | 1019 | 2019 | 3019 | 2023-04-26 00:00:00 | 2023-05-15 00:00:00 | 2023-05-30 00:00:00 | 2023-06-15 00:00:00 | 2023-06-20 00:00:00 | Completed early | - | 0 | 18
20 | John Brown | Anna Green | Team Delta | 11 | 4 | 7 | 2023-04-20 00:00:00 | 2023-04-30 00:00:00 | 1020 | 1020 | 2020 | 3020 | 2023-05-01 00:00:00 | 2023-05-20 00:00:00 | 2023-06-05 00:00:00 | 2023-06-20 00:00:00 | 2023-06-25 00:00:00 | On hold | - | 0 | 19
21 | Susan Davis | Paul Adams | Team Epsilon | 13 | 5 | 8 | 2023-05-01 00:00:00 | 2023-05-10 00:00:00 | 1021 | 1021 | 2021 | 3021 | 2023-05-11 00:00:00 | 2023-06-01 00:00:00 | 2023-06-15 00:00:00 | 2023-07-01 00:00:00 | 2023-07-05 00:00:00 | Completed on time | - | 0 | 20
22 | Susan Davis | Paul Adams | Team Epsilon | 9 | 3 | 6 | 2023-05-05 00:00:00 | 2023-05-15 00:00:00 | 1022 | 1022 | 2022 | 3022 | 2023-05-16 00:00:00 | 2023-06-05 00:00:00 | 2023-06-20 00:00:00 | 2023-07-05 00:00:00 | 2023-07-10 00:00:00 | Minor delays | - | 0 | 21
23 | Susan Davis | Paul Adams | Team Epsilon | 12 | 4 | 8 | 2023-05-10 00:00:00 | 2023-05-20 00:00:00 | 1023 | 1023 | 2023 | 3023 | 2023-05-21 00:00:00 | 2023-06-10 00:00:00 | 2023-06-25 00:00:00 | 2023-07-10 00:00:00 | 2023-07-15 00:00:00 | On track | - | 0 | 22
24 | Susan Davis | Paul Adams | Team Epsilon | 10 | 4 | 6 | 2023-05-15 00:00:00 | 2023-05-25 00:00:00 | 1024 | 1024 | 2024 | 3024 | 2023-05-26 00:00:00 | 2023-06-15 00:00:00 | 2023-06-30 00:00:00 | 2023-07-15 00:00:00 | 2023-07-20 00:00:00 | Completed early | - | 0 | 23
25 | Susan Davis | Paul Adams | Team Epsilon | 8 | 2 | 6 | 2023-05-20 00:00:00 | 2023-05-30 00:00:00 | 1025 | 1025 | 2025 | 3025 | 2023-05-31 00:00:00 | 2023-06-20 00:00:00 | 2023-07-05 00:00:00 | 2023-07-20 00:00:00 | 2023-07-25 00:00:00 | On hold | - | 0 | 24
26 | James Wilson | Emily Johnson | Team Zeta | 10 | 4 | 6 | 2023-06-01 00:00:00 | 2023-06-10 00:00:00 | 1026 | 1026 | 2026 | 3026 | 2023-06-11 00:00:00 | 2023-07-01 00:00:00 | 2023-07-15 00:00:00 | 2023-08-01 00:00:00 | 2023-08-05 00:00:00 | Completed on time | - | 0 | 25
27 | James Wilson | Emily Johnson | Team Zeta | 11 | 5 | 6 | 2023-06-05 00:00:00 | 2023-06-15 00:00:00 | 1027 | 1027 | 2027 | 3027 | 2023-06-16 00:00:00 | 2023-07-05 00:00:00 | 2023-07-20 00:00:00 | 2023-08-05 00:00:00 | 2023-08-10 00:00:00 | Minor delays | - | 0 | 26
28 | James Wilson | Emily Johnson | Team Zeta | 13 | 6 | 7 | 2023-06-10 00:00:00 | 2023-06-20 00:00:00 | 1028 | 1028 | 2028 | 3028 | 2023-06-21 00:00:00 | 2023-07-10 00:00:00 | 2023-07-25 00:00:00 | 2023-08-10 00:00:00 | 2023-08-15 00:00:00 | On track | - | 0 | 27
29 | James Wilson | Emily Johnson | Team Zeta | 9 | 3 | 6 | 2023-06-15 00:00:00 | 2023-06-25 00:00:00 | 1029 | 1029 | 2029 | 3029 | 2023-06-26 00:00:00 | 2023-07-15 00:00:00 | 2023-07-30 00:00:00 | 2023-08-15 00:00:00 | 2023-08-20 00:00:00 | Completed early | - | 0 | 28
30 | James Wilson | Emily Johnson | Team Zeta | 12 | 5 | 7 | 2023-06-20 00:00:00 | 2023-06-30 00:00:00 | 1030 | 1030 | 2030 | 3030 | 2023-07-01 00:00:00 | 2023-07-20 00:00:00 | 2023-08-05 00:00:00 | 2023-08-20 00:00:00 | 2023-08-25 00:00:00 | On hold | - | 0 | 29
31 | Chris Johnson | Nina Brown | Team Eta | 10 | 4 | 6 | 2023-07-01 00:00:00 | 2023-07-10 00:00:00 | 1031 | 1031 | 2031 | 3031 | 2023-07-11 00:00:00 | 2023-08-01 00:00:00 | 2023-08-15 00:00:00 | 2023-09-01 00:00:00 | 2023-09-05 00:00:00 | Completed on time | - | 0 | 30
32 | Chris Johnson | Nina Brown | Team Eta | 9 | 3 | 6 | 2023-07-05 00:00:00 | 2023-07-15 00:00:00 | 1032 | 1032 | 2032 | 3032 | 2023-07-16 00:00:00 | 2023-08-05 00:00:00 | 2023-08-20 00:00:00 | 2023-09-05 00:00:00 | 2023-09-10 00:00:00 | Minor delays | - | 0 | 31
33 | Chris Johnson | Nina Brown | Team Eta | 11 | 5 | 6 | 2023-07-10 00:00:00 | 2023-07-20 00:00:00 | 1033 | 1033 | 2033 | 3033 | 2023-07-21 00:00:00 | 2023-08-10 00:00:00 | 2023-08-25 00:00:00 | 2023-09-10 00:00:00 | 2023-09-15 00:00:00 | On track | - | 0 | 32
34 | Chris Johnson | Nina Brown | Team Eta | 8 | 3 | 5 | 2023-07-15 00:00:00 | 2023-07-25 00:00:00 | 1034 | 1034 | 2034 | 3034 | 2023-07-26 00:00:00 | 2023-08-15 00:00:00 | 2023-08-30 00:00:00 | 2023-09-15 00:00:00 | 2023-09-20 00:00:00 | Completed early | - | 0 | 33
35 | Chris Johnson | Nina Brown | Team Eta | 13 | 6 | 7 | 2023-07-20 00:00:00 | 2023-07-30 00:00:00 | 1035 | 1035 | 2035 | 3035 | 2023-07-31 00:00:00 | 2023-08-20 00:00:00 | 2023-09-05 00:00:00 | 2023-09-20 00:00:00 | 2023-09-25 00:00:00 | On hold | - | 0 | 34
36 | Karen Taylor | Steve Martin | Team Theta | 10 | 4 | 6 | 2023-08-01 00:00:00 | 2023-08-10 00:00:00 | 1036 | 1036 | 2036 | 3036 | 2023-08-11 00:00:00 | 2023-09-01 00:00:00 | 2023-09-15 00:00:00 | 2023-10-01 00:00:00 | 2023-10-05 00:00:00 | Completed on time | - | 0 | 35
37 | Karen Taylor | Steve Martin | Team Theta | 11 | 5 | 6 | 2023-08-05 00:00:00 | 2023-08-15 00:00:00 | 1037 | 1037 | 2037 | 3037 | 2023-08-16 00:00:00 | 2023-09-05 00:00:00 | 2023-09-20 00:00:00 | 2023-10-05 00:00:00 | 2023-10-10 00:00:00 | Minor delays | - | 0 | 36
38 | Karen Taylor | Steve Martin | Team Theta | 9 | 3 | 6 | 2023-08-10 00:00:00 | 2023-08-20 00:00:00 | 1038 | 1038 | 2038 | 3038 | 2023-08-21 00:00:00 | 2023-09-10 00:00:00 | 2023-09-25 00:00:00 | 2023-10-10 00:00:00 | 2023-10-15 00:00:00 | On track | - | 0 | 37
39 | Karen Taylor | Steve Martin | Team Theta | 12 | 5 | 7 | 2023-08-15 00:00:00 | 2023-08-25 00:00:00 | 1039 | 1039 | 2039 | 3039 | 2023-08-26 00:00:00 | 2023-09-15 00:00:00 | 2023-09-30 00:00:00 | 2023-10-15 00:00:00 | 2023-10-20 00:00:00 | Completed early | - | 0 | 38
40 | Karen Taylor | Steve Martin | Team Theta | 10 | 4 | 6 | 2023-08-20 00:00:00 | 2023-08-30 00:00:00 | 1040 | 1040 | 2040 | 3040 | 2023-08-31 00:00:00 | 2023-09-20 00:00:00 | 2023-10-05 00:00:00 | 2023-10-20 00:00:00 | 2023-10-25 00:00:00 | On hold | - | 0 | 39
41 | Paul Edwards | Maria Hernandez | Team Iota | 9 | 3 | 6 | 2023-09-01 00:00:00 | 2023-09-10 00:00:00 | 1041 | 1041 | 2041 | 3041 | 2023-09-11 00:00:00 | 2023-10-01 00:00:00 | 2023-10-15 00:00:00 | 2023-11-01 00:00:00 | 2023-11-05 00:00:00 | Completed on time | - | 0 | 40
42 | Paul Edwards | Maria Hernandez | Team Iota | 11 | 5 | 6 | 2023-09-05 00:00:00 | 2023-09-15 00:00:00 | 1042 | 1042 | 2042 | 3042 | 2023-09-16 00:00:00 | 2023-10-05 00:00:00 | 2023-10-20 00:00:00 | 2023-11-05 00:00:00 | 2023-11-10 00:00:00 | Minor delays | - | 0 | 41
43 | Paul Edwards | Maria Hernandez | Team Iota | 13 | 6 | 7 | 2023-09-10 00:00:00 | 2023-09-20 00:00:00 | 1043 | 1043 | 2043 | 3043 | 2023-09-21 00:00:00 | 2023-10-10 00:00:00 | 2023-10-25 00:00:00 | 2023-11-10 00:00:00 | 2023-11-15 00:00:00 | On track | - | 0 | 42
44 | Paul Edwards | Maria Hernandez | Team Iota | 10 | 4 | 6 | 2023-09-15 00:00:00 | 2023-09-25 00:00:00 | 1044 | 1044 | 2044 | 3044 | 2023-09-26 00:00:00 | 2023-10-15 00:00:00 | 2023-10-30 00:00:00 | 2023-11-15 00:00:00 | 2023-11-20 00:00:00 | Completed early | - | 0 | 43
45 | Paul Edwards | Maria Hernandez | Team Iota | 8 | 2 | 6 | 2023-09-20 00:00:00 | 2023-09-30 00:00:00 | 1045 | 1045 | 2045 | 3045 | 2023-10-01 00:00:00 | 2023-10-20 00:00:00 | 2023-11-05 00:00:00 | 2023-11-20 00:00:00 | 2023-11-25 00:00:00 | On hold | - | 0 | 44
46 | David Clark | Julia Rogers | Team Kappa | 12 | 5 | 7 | 2023-10-01 00:00:00 | 2023-10-10 00:00:00 | 1046 | 1046 | 2046 | 3046 | 2023-10-11 00:00:00 | 2023-11-01 00:00:00 | 2023-11-15 00:00:00 | 2023-12-01 00:00:00 | 2023-12-05 00:00:00 | Completed on time | - | 0 | 45
47 | David Clark | Julia Rogers | Team Kappa | 10 | 4 | 6 | 2023-10-05 00:00:00 | 2023-10-15 00:00:00 | 1047 | 1047 | 2047 | 3047 | 2023-10-16 00:00:00 | 2023-11-05 00:00:00 | 2023-11-20 00:00:00 | 2023-12-05 00:00:00 | 2023-12-10 00:00:00 | Minor delays | - | 0 | 46
48 | David Clark | Julia Rogers | Team Kappa | 14 | 6 | 8 | 2023-10-10 00:00:00 | 2023-10-20 00:00:00 | 1048 | 1048 | 2048 | 3048 | 2023-10-21 00:00:00 | 2023-11-10 00:00:00 | 2023-11-25 00:00:00 | 2023-12-10 00:00:00 | 2023-12-15 00:00:00 | On track | - | 0 | 47
49 | David Clark | Julia Rogers | Team Kappa | 9 | 3 | 6 | 2023-10-15 00:00:00 | 2023-10-25 00:00:00 | 1049 | 1049 | 2049 | 3049 | 2023-10-26 00:00:00 | 2023-11-15 00:00:00 | 2023-11-30 00:00:00 | 2023-12-15 00:00:00 | 2023-12-20 00:00:00 | Completed early | - | 0 | 48
50 | David Clark | Julia Rogers | Team Kappa | 11 | 4 | 7 | 2023-10-20 00:00:00 | 2023-10-30 00:00:00 | 1050 | 1050 | 2050 | 3050 | 2023-10-31 00:00:00 | 2023-11-20 00:00:00 | 2023-12-05 00:00:00 | 2023-12-20 00:00:00 | 12/25/2023 |  | - | 0 | 49

## Sheet2
First Name | Last Name | TechM mail Id | Profile Link | Email Id | Mobile | External | Submission date | Exp | Location | City | Country | Date of Joining | Customer Billing Start date | Tech M Interview Date | Interview Feedback Link | Customer Interview Date | Customer Feedback | Status | Remarks | Remarks2 | Sourced to Client date | Transition Month | ADM | Team | App Name | Skill | Technology Skill | Skill Level | FTE/Subcon
John | Doe | john.doe@techm.com | link1 | john.doe@gmail.com | 1234567890 | Yes | 2023-01-01 00:00:00 | 5 | New York | New York | USA | 2023-02-01 00:00:00 | 2023-02-15 00:00:00 | 2023-01-15 00:00:00 | link1 | 2023-01-20 00:00:00 | link1 | Selected | - | - | 2023-01-25 00:00:00 | January | John Doe | Team Alpha | AppA | Java | Advanced | 5 | FTE
Jane | Smith | jane.smith@techm.com | link2 | jane.smith@gmail.com | 1234567891 | No | 2023-01-02 00:00:00 | 7 | San Francisco | San Francisco | USA | 2023-02-02 00:00:00 | 2023-02-16 00:00:00 | 2023-01-16 00:00:00 | link2 | 2023-01-21 00:00:00 | link2 | Selected | - | - | 2023-01-26 00:00:00 | January | Jane Smith | Team Beta | AppB | Python | Intermediate | 4 | Subcon
Mike | Jones | mike.jones@techm.com | link3 | mike.jones@gmail.com | 1234567892 | Yes | 2023-01-03 00:00:00 | 6 | Chicago | Chicago | USA | 2023-02-03 00:00:00 | 2023-02-17 00:00:00 | 2023-01-17 00:00:00 | link3 | 2023-01-22 00:00:00 | link3 | Selected | - | - | 2023-01-27 00:00:00 | January | Mike Jones | Team Gamma | AppC | JavaScript | Advanced | 5 | FTE
Lisa | Taylor | lisa.taylor@techm.com | link4 | lisa.taylor@gmail.com | 1234567893 | No | 2023-01-04 00:00:00 | 8 | Boston | Boston | USA | 2023-02-04 00:00:00 | 2023-02-18 00:00:00 | 2023-01-18 00:00:00 | link4 | 2023-01-23 00:00:00 | link4 | Selected | - | - | 2023-01-28 00:00:00 | January | Lisa Taylor | Team Delta | AppD | C# | Intermediate | 4 | Subcon
Steve | Brown | steve.brown@techm.com | link5 | steve.brown@gmail.com | 1234567894 | Yes | 2023-01-05 00:00:00 | 5 | Austin | Austin | USA | 2023-02-05 00:00:00 | 2023-02-19 00:00:00 | 2023-01-19 00:00:00 | link5 | 2023-01-24 00:00:00 | link5 | Selected | - | - | 2023-01-29 00:00:00 | January | Steve Brown | Team Epsilon | AppE | SQL | Advanced | 5 | FTE
Sarah | White | sarah.white@techm.com | link6 | sarah.white@gmail.com | 1234567895 | No | 2023-01-06 00:00:00 | 7 | Dallas | Dallas | USA | 2023-02-06 00:00:00 | 2023-02-20 00:00:00 | 2023-01-20 00:00:00 | link6 | 2023-01-25 00:00:00 | link6 | Selected | - | - | 2023-01-30 00:00:00 | January | Sarah White | Team Zeta | AppF | PHP | Intermediate | 4 | Subcon
David | Harris | david.harris@techm.com | link7 | david.harris@gmail.com | 1234567896 | Yes | 2023-01-07 00:00:00 | 6 | Seattle | Seattle | USA | 2023-02-07 00:00:00 | 2023-02-21 00:00:00 | 2023-01-21 00:00:00 | link7 | 2023-01-26 00:00:00 | link7 | Selected | - | - | 2023-01-31 00:00:00 | January | David Harris | Team Eta | AppG | Ruby | Advanced | 5 | FTE
Emily | Clark | emily.clark@techm.com | link8 | emily.clark@gmail.com | 1234567897 | No | 2023-01-08 00:00:00 | 8 | Denver | Denver | USA | 2023-02-08 00:00:00 | 2023-02-22 00:00:00 | 2023-01-22 00:00:00 | link8 | 2023-01-27 00:00:00 | link8 | Selected | - | - | 2023-02-01 00:00:00 | February | Emily Clark | Team Theta | AppH | C++ | Intermediate | 4 | Subcon
James | Martin | james.martin@techm.com | link9 | james.martin@gmail.com | 1234567898 | Yes | 2023-01-09 00:00:00 | 5 | Houston | Houston | USA | 2023-02-09 00:00:00 | 2023-02-23 00:00:00 | 2023-01-23 00:00:00 | link9 | 2023-01-28 00:00:00 | link9 | Selected | - | - | 2023-02-02 00:00:00 | February | James Martin | Team Iota | AppI | HTML | Advanced | 5 | FTE
Mary | Lewis | mary.lewis@techm.com | link10 | mary.lewis@gmail.com | 1234567899 | No | 2023-01-10 00:00:00 | 7 | Miami | Miami | USA | 2023-02-10 00:00:00 | 2023-02-24 00:00:00 | 2023-01-24 00:00:00 | link10 | 2023-01-29 00:00:00 | link10 | Selected | - | - | 2023-02-03 00:00:00 | February | Mary Lewis | Team Kappa | AppJ | CSS | Intermediate | 4 | Subcon
Robert | Walker | robert.walker@techm.com | link11 | robert.walker@gmail.com | 1234567800 | Yes | 2023-01-11 00:00:00 | 6 | Orlando | Orlando | USA | 2023-02-11 00:00:00 | 2023-02-25 00:00:00 | 2023-01-25 00:00:00 | link11 | 2023-01-30 00:00:00 | link11 | Selected | - | - | 2023-02-04 00:00:00 | February | Robert Walker | Team Alpha | AppK | Python | Advanced | 5 | FTE
Laura | Hall | laura.hall@techm.com | link12 | laura.hall@gmail.com | 1234567801 | No | 2023-01-12 00:00:00 | 8 | Los Angeles | Los Angeles | USA | 2023-02-12 00:00:00 | 2023-02-26 00:00:00 | 2023-01-26 00:00:00 | link12 | 2023-01-31 00:00:00 | link12 | Selected | - | - | 2023-02-05 00:00:00 | February | Laura Hall | Team Beta | AppL | Java | Intermediate | 4 | Subcon
Daniel | Allen | daniel.allen@techm.com | link13 | daniel.allen@gmail.com | 1234567802 | Yes | 2023-01-13 00:00:00 | 5 | San Diego | San Diego | USA | 2023-02-13 00:00:00 | 2023-02-27 00:00:00 | 2023-01-27 00:00:00 | link13 | 2023-02-01 00:00:00 | link13 | Selected | - | - | 2023-02-06 00:00:00 | February | Daniel Allen | Team Gamma | AppM | JavaScript | Advanced | 5 | FTE
Nancy | Young | nancy.young@techm.com | link14 | nancy.young@gmail.com | 1234567803 | No | 2023-01-14 00:00:00 | 7 | Las Vegas | Las Vegas | USA | 2023-02-14 00:00:00 | 2023-02-28 00:00:00 | 2023-01-28 00:00:00 | link14 | 2023-02-02 00:00:00 | link14 | Selected | - | - | 2023-02-07 00:00:00 | February | Nancy Young | Team Delta | AppN | C# | Intermediate | 4 | Subcon
Kevin | Hernandez | kevin.hernandez@techm.com | link15 | kevin.hernandez@gmail.com | 1234567804 | Yes | 2023-01-15 00:00:00 | 6 | Portland | Portland | USA | 2023-02-15 00:00:00 | 2023-03-01 00:00:00 | 2023-01-29 00:00:00 | link15 | 2023-02-03 00:00:00 | link15 | Selected | - | - | 2023-02-08 00:00:00 | February | Kevin Hernandez | Team Epsilon | AppO | SQL | Advanced | 5 | FTE
Karen | King | karen.king@techm.com | link16 | karen.king@gmail.com | 1234567805 | No | 2023-01-16 00:00:00 | 8 | Phoenix | Phoenix | USA | 2023-02-16 00:00:00 | 2023-03-02 00:00:00 | 2023-01-30 00:00:00 | link16 | 2023-02-04 00:00:00 | link16 | Selected | - | - | 2023-02-09 00:00:00 | February | Karen King | Team Zeta | AppP | PHP | Intermediate | 4 | Subcon
Brian | Wright | brian.wright@techm.com | link17 | brian.wright@gmail.com | 1234567806 | Yes | 2023-01-17 00:00:00 | 5 | San Jose | San Jose | USA | 2023-02-17 00:00:00 | 2023-03-03 00:00:00 | 2023-01-31 00:00:00 | link17 | 2023-02-05 00:00:00 | link17 | Selected | - | - | 2023-02-10 00:00:00 | February | Brian Wright | Team Eta | AppQ | Ruby | Advanced | 5 | FTE
Amanda | Lopez | amanda.lopez@techm.com | link18 | amanda.lopez@gmail.com | 1234567807 | No | 2023-01-18 00:00:00 | 7 | Sacramento | Sacramento | USA | 2023-02-18 00:00:00 | 2023-03-04 00:00:00 | 2023-02-01 00:00:00 | link18 | 2023-02-06 00:00:00 | link18 | Selected | - | - | 2023-02-11 00:00:00 | February | Amanda Lopez | Team Theta | AppR | C++ | Intermediate | 4 | Subcon
George | Hill | george.hill@techm.com | link19 | george.hill@gmail.com | 1234567808 | Yes | 2023-01-19 00:00:00 | 6 | Columbus | Columbus | USA | 2023-02-19 00:00:00 | 2023-03-05 00:00:00 | 2023-02-02 00:00:00 | link19 | 2023-02-07 00:00:00 | link19 | Selected | - | - | 2023-02-12 00:00:00 | February | George Hill | Team Iota | AppS | HTML | Advanced | 5 | FTE
Susan | Scott | susan.scott@techm.com | link20 | susan.scott@gmail.com | 1234567809 | No | 2023-01-20 00:00:00 | 8 | Charlotte | Charlotte | USA | 2023-02-20 00:00:00 | 2023-03-06 00:00:00 | 2023-02-03 00:00:00 | link20 | 2023-02-08 00:00:00 | link20 | Selected | - | - | 2023-02-13 00:00:00 | February | Susan Scott | Team Kappa | AppT | CSS | Intermediate | 4 | Subcon

## Sheet3
Profile uploaded in Large Deal Coupa | Details sent to VAIRA | Tech M allocation | Coupa Request Sent to PMO | Emp ID | Band | Resource Name | Location | App Name | Skills | Tech M E-mail ID | UPS E-mail ID | Phone # | New RM change is completed - Yes or NO | VPN Ticket ID | Citrix Ticket ID | RM/IBU Head approval - Aproved/ Pending | CW ID | Challenge Q&A Setup | UPS E-mail access | AD ID | UPS Laptop | Static IP Whitelisting | Citrix installed in system | VPN installed in system | APRS e-mail | RSA activation | Citrix license | Check point VPN Access | Zscalar policy | UPS Teams access | Remote Desktop IP address | ITAS Access | PAR ID | Coupa end date | Data Protection (SS1369) | Sexual Harassment (POSH) | Code of Ethical Business Conduct Mandate (CEBC) | Securing Our Business (SS18449) | Logistics 101 | Hacker Rank Certification | Added in Vaira's List | Lead Resource | 2nd POC | TechM Laptop (Y/N) | Citrix approval-ISG | Citrix approval-RM | Citrix approval-IBU Head | VPN | Citrix approval-RM.1 | Citrix approval-IBU Head.1 | UPS Laptop (Y/N) | KT Start Date | Remarks | Project
Yes | Yes | Yes | Yes | 101 | B1 | John Doe | New York | AppA | Java | john.doe@techm.com | john.doe@ups.com | 1234567890 | Yes | 101-VPN | 101-Citrix | Approved | 1001 | Yes | Yes | AD101 | Yes | Yes | Yes | Yes | john.doe@ups.com | Active | Yes | Yes | Yes | Yes | Yes | 192.168.1.1 | Yes | PAR101 | 2024-12-31 00:00:00 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Y | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2024-01-01 00:00:00
Yes | Yes | Yes | Yes | 102 | B2 | Jane Smith | San Francisco | AppB | Python | jane.smith@techm.com | jane.smith@ups.com | 1234567891 | No | 102-VPN | 102-Citrix | Pending | 1002 | No | Yes | AD102 | No | No | No | No | jane.smith@ups.com | Active | No | No | No | No | No | 192.168.1.2 | No | PAR102 | 2024-12-31 00:00:00 | No | No | No | No | No | No | No | No | No | No | Y | Approved | Approved | Pending | No | Approved | Pending | No | 2024-01-02 00:00:00
Yes | Yes | Yes | Yes | 103 | B3 | Mike Jones | Chicago | AppC | JavaScript | mike.jones@techm.com | mike.jones@ups.com | 1234567892 | Yes | 103-VPN | 103-Citrix | Approved | 1003 | Yes | Yes | AD103 | Yes | Yes | Yes | Yes | mike.jones@ups.com | Active | Yes | Yes | Yes | Yes | Yes | 192.168.1.3 | Yes | PAR103 | 2024-12-31 00:00:00 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Y | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2024-01-03 00:00:00
Yes | Yes | Yes | Yes | 104 | B1 | Lisa Taylor | Boston | AppD | C# | lisa.taylor@techm.com | lisa.taylor@ups.com | 1234567893 | No | 104-VPN | 104-Citrix | Pending | 1004 | No | Yes | AD104 | No | No | No | No | lisa.taylor@ups.com | Active | No | No | No | No | No | 192.168.1.4 | No | PAR104 | 2024-12-31 00:00:00 | No | No | No | No | No | No | No | No | No | No | Y | Approved | Approved | Pending | No | Approved | Pending | No | 2024-01-04 00:00:00
Yes | Yes | Yes | Yes | 105 | B2 | Steve Brown | Austin | AppE | SQL | steve.brown@techm.com | steve.brown@ups.com | 1234567894 | Yes | 105-VPN | 105-Citrix | Approved | 1005 | Yes | Yes | AD105 | Yes | Yes | Yes | Yes | steve.brown@ups.com | Active | Yes | Yes | Yes | Yes | Yes | 192.168.1.5 | Yes | PAR105 | 2024-12-31 00:00:00 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Y | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2024-01-05 00:00:00
Yes | Yes | Yes | Yes | 106 | B3 | Sarah White | Dallas | AppF | PHP | sarah.white@techm.com | sarah.white@ups.com | 1234567895 | No | 106-VPN | 106-Citrix | Pending | 1006 | No | Yes | AD106 | No | No | No | No | sarah.white@ups.com | Active | No | No | No | No | No | 192.168.1.6 | No | PAR106 | 2024-12-31 00:00:00 | No | No | No | No | No | No | No | No | No | No | Y | Approved | Approved | Pending | No | Approved | Pending | No | 2024-01-06 00:00:00
Yes | Yes | Yes | Yes | 107 | B1 | David Harris | Seattle | AppG | Ruby | david.harris@techm.com | david.harris@ups.com | 1234567896 | Yes | 107-VPN | 107-Citrix | Approved | 1007 | Yes | Yes | AD107 | Yes | Yes | Yes | Yes | david.harris@ups.com | Active | Yes | Yes | Yes | Yes | Yes | 192.168.1.7 | Yes | PAR107 | 2024-12-31 00:00:00 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Y | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2024-01-07 00:00:00
Yes | Yes | Yes | Yes | 108 | B2 | Emily Clark | Denver | AppH | C++ | emily.clark@techm.com | emily.clark@ups.com | 1234567897 | No | 108-VPN | 108-Citrix | Pending | 1008 | No | Yes | AD108 | No | No | No | No | emily.clark@ups.com | Active | No | No | No | No | No | 192.168.1.8 | No | PAR108 | 2024-12-31 00:00:00 | No | No | No | No | No | No | No | No | No | No | Y | Approved | Approved | Pending | No | Approved | Pending | No | 2024-01-08 00:00:00
Yes | Yes | Yes | Yes | 109 | B3 | James Martin | Houston | AppI | HTML | james.martin@techm.com | james.martin@ups.com | 1234567898 | Yes | 109-VPN | 109-Citrix | Approved | 1009 | Yes | Yes | AD109 | Yes | Yes | Yes | Yes | james.martin@ups.com | Active | Yes | Yes | Yes | Yes | Yes | 192.168.1.9 | Yes | PAR109 | 2024-12-31 00:00:00 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Y | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2024-01-09 00:00:00
Yes | Yes | Yes | Yes | 110 | B1 | Mary Lewis | Miami | AppJ | CSS | mary.lewis@techm.com | mary.lewis@ups.com | 1234567899 | No | 110-VPN | 110-Citrix | Pending | 1010 | No | Yes | AD110 | No | No | No | No | mary.lewis@ups.com | Active | No | No | No | No | No | 192.168.1.10 | No | PAR110 | 2024-12-31 00:00:00 | No | No | No | No | No | No | No | No | No | No | Y | Approved | Approved | Pending | No | Approved | Pending | No | 2024-01-10 00:00:00
Yes | Yes | Yes | Yes | 111 | B2 | Robert Walker | Orlando | AppK | Python | robert.walker@techm.com | robert.walker@ups.com | 1234567800 | Yes | 111-VPN | 111-Citrix | Approved | 1011 | Yes | Yes | AD111 | Yes | Yes | Yes | Yes | robert.walker@ups.com | Active | Yes | Yes | Yes | Yes | Yes | 192.168.1.11 | Yes | PAR111 | 2024-12-31 00:00:00 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Y | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2024-01-11 00:00:00
Yes | Yes | Yes | Yes | 112 | B3 | Linda Young | Atlanta | AppL | Java | linda.young@techm.com | linda.young@ups.com | 1234567801 | No | 112-VPN | 112-Citrix | Pending | 1012 | No | Yes | AD112 | No | No | No | No | linda.young@ups.com | Active | No | No | No | No | No | 192.168.1.12 | No | PAR112 | 2024-12-31 00:00:00 | No | No | No | No | No | No | No | No | No | No | Y | Approved | Approved | Pending | No | Approved | Pending | No | 2024-01-12 00:00:00
Yes | Yes | Yes | Yes | 113 | B1 | Charles Hall | Phoenix | AppM | JavaScript | charles.hall@techm.com | charles.hall@ups.com | 1234567802 | Yes | 113-VPN | 113-Citrix | Approved | 1013 | Yes | Yes | AD113 | Yes | Yes | Yes | Yes | charles.hall@ups.com | Active | Yes | Yes | Yes | Yes | Yes | 192.168.1.13 | Yes | PAR113 | 2024-12-31 00:00:00 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Y | Approved | Approved | Approved | Yes | Approved | Approved | Yes | 2024-01-13 00:00:00
Yes | Yes | Yes | Yes | 114 | B2 | Amy Hernandez | Philadelphia | AppN | C# | amy.hernandez@techm.com | amy.hernandez@ups.com | 1234567803 | No | 114-VPN | 114-Citrix | Pending | 1014 | No | Yes | AD114 | No | No | No | No | amy.hernandez@ups.com | Active | No | No | No | No | No | 192.168.1.14 | No | PAR114 | 2024-12-31 00:00:00 | No | No | No | No | No | No | No | No | No | No | Y | Approved | Approved | Pending | No | Approved | Pending | No | 2024-01-14 00:00:00
Yes | Yes | Yes | Yes | 115 | B3 | Michael Allen | Detroit | AppO | SQL | michael.allen@techm.com | michael.allen@ups.com | 1234567804 | Yes | 115-VPN | 115-Citrix | Approved | 1015 | Yes | Yes | AD115 | Yes | Yes | Yes | Yes | michael.allen@ups.com | Active | Yes | Yes | Yes | Yes | Yes | 192.168.1.15 | Yes | PAR115 | 2024-12-31 00:00:00 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Y | Approved | Approved | Approved | Yes

## Sheet4
Date | Team | Resource Name | Issue Description | Owner | TechM - SPOC | Priority | Status | Resolution Comments
2024-01-01 00:00:00 | Team A | John Doe | Login issues | Emily Clark | Mike Johnson | High | Open | -
2024-01-02 00:00:00 | Team B | Jane Smith | Network connectivity | Steve Brown | Sarah White | Medium | In Progress | -
2024-01-03 00:00:00 | Team C | Mike Jones | Software installation | Robert Walker | David Harris | Low | Resolved | Reinstalled software
2024-01-04 00:00:00 | Team D | Lisa Taylor | System crash | Linda Young | Emily Clark | High | Open | -
2024-01-05 00:00:00 | Team E | Steve Brown | Printer not working | Charles Hall | Jane Smith | Medium | Closed | Replaced printer
2024-01-06 00:00:00 | Team F | Sarah White | Email not syncing | Patricia King | Mike Johnson | Low | Resolved | Email configuration updated
2024-01-07 00:00:00 | Team G | David Harris | Slow performance | Barbara Wright | Linda Young | High | In Progress | Checking system resources
2024-01-08 00:00:00 | Team H | Emily Clark | Access denied | George Hill | Robert Walker | Medium | Open | -
2024-01-09 00:00:00 | Team I | James Martin | Password reset | Amy Hernandez | David Harris | Low | Resolved | Password reset
2024-01-10 00:00:00 | Team J | Mary Lewis | VPN issues | Michael Allen | Emily Clark | High | Open | -
2024-01-11 00:00:00 | Team K | Robert Walker | Database error | Lisa Taylor | Charles Hall | Medium | Closed | Fixed database configuration
2024-01-12 00:00:00 | Team L | Linda Young | Screen flickering | Steve Brown | Barbara Wright | Low | Resolved | Updated graphics driver
2024-01-13 00:00:00 | Team M | Charles Hall | Missing files | Patricia King | George Hill | High | In Progress | Recovering files
2024-01-14 00:00:00 | Team N | Amy Hernandez | Application crash | Sarah White | Robert Walker | Medium | Open | -
2024-01-15 00:00:00 | Team O | Michael Allen | Network lag | David Harris | Mike Johnson | Low | Resolved | Optimized network settings
2024-01-16 00:00:00 | Team P | Patricia King | System freeze | Emily Clark | Steve Brown | High | Open | -
2024-01-17 00:00:00 | Team Q | Barbara Wright | Security alert | Linda Young | Patricia King | Medium | Closed | Updated security patches
2024-01-18 00:00:00 | Team R | George Hill | Backup failure | Amy Hernandez | Michael Allen | Low | Resolved | Backup system reconfigured
2024-01-19 00:00:00 | Team S | Matthew Young | Software update issue | James Martin | Lisa Taylor | High | In Progress | Reverting to previous version
2024-01-20 00:00:00 | Team T | Jennifer Adams | Email delivery failure | Robert Walker | Sarah White | Medium | Open | -